## Working route
Blackboard Group No 01 Class NDD | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP
reference and relative due dates |  | Update E3 to your PM class date | =====> | 2023-11-21 | Monday Nov.20 |  |  | PM class date plus | 9 | days |  |  | PM class date plus | 14 | days |  |  | PM class date plus | 21 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | 2023-12-14
Each Team member | Your Project Mgmt notes on what each Process Group means to you when doing this project. | Share with team by uploading PM-Notes-myName.docx to Bb ## team channel's Files |  | Wednesday Nov.22 | TO DO | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details |  | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details |  | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details
Team Meeting Agenda ==> | create MS Teams Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 | Thursday Nov.23 --- Wednesday Nov.22 | DONE | review progress, refine Plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. |  | Monday Nov.27 | TO DO | Team decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Saturday Dec.2 | TO DO | Team decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Saturday Dec.9 | TO DO | Submit final version of artefacts from Teams to Blackboard in a .ZIP archive. Backup Team's files. | updated all DONE items with actual hours. |  | Monday Dec.11 | TO DO
| request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Friday Nov.24 |  | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Monday Nov.27 | TO DO | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Saturday Dec.2 | TO DO | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Saturday Dec.9 | TO DO
Ying Cheung Ellis Fung Fundamentals | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | https://seneca.sharepoint.com/:w:/s/CPR101Mondays-Group1/EWMQz5ZhnsxHkA0aXxAmxrcBTaVGYuPkF9dL4qyPNgzLtw?e=eScR0Q |  | Thursday Nov.23 |  | * Notes * Version 1 development * Version 1 test examples * Upload final version to root folder | * PM-Notes-Ying Cheung Ellis Fung.docx * fundamentalsv1_test_cases.xlsx * fundamentals.c * fundamentals.h (Done when approved by Tester) | 3.75 | Friday Nov.24 ---------- Thursday Nov.23 | DONE | * Notes * Version 2 development * Version 2 test examples * Upload final version to git repository | * PM-Notes-Ying Cheung Ellis Fung.docx * fundamentalsv2_test_cases.xlsx * fundamentals.c * fundamentals.h (Done when approved by Tester) | 3.25 | Sunday Nov.26 | DONE | * Notes * Version 3 development * Version 3 test examples * Upload final version to git repository | * PM-Notes-Ying Cheung Ellis Fung.docx * fundamentalsv3_test_cases.xlsx * fundamentals.c * fundamentals.h (Done when approved by Tester) | 3.25 | Friday Dec.01 | DONE |  |  |  | Tuesday Dec.12
Erfan Abbasgholi Zadeh Manipulations | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader |  |  | Thursday Nov.23 |  | * Notes * Version 1 development * Version 1 test examples * Upload final version to root folder | * PM-Notes-Erfan Abbasgholi Zadeh.docx * manipulationsv1_test_cases.xlsx * manipulations.c * manipulations.h (Done when approved by Tester) | 3.75 | Friday Nov.24 ---------- Firday Nov.24 | DONE | * Notes * Version 2 development * Version 2 test examples * Upload final version to git repository | * PM-Notes-Erfan Abbasgholi Zadeh.docx * manipulationsv2_test_cases.xlsx * manipulations.c * manipulations.h (Done when approved by Tester) | 3.25 | Sunday Nov.26 | DONE | * Notes * Version 3 development * Version 3 test examples * Upload final version to git repository | * PM-Notes-Erfan Abbasgholi Zadeh.docx * manipulationsv3_test_cases.xlsx * manipulations.c * manipulations.h (Done when approved by Tester) | 3.25 | Friday Dec.01 | DONE |  |  |  | Tuesday Dec.12
Alexander Raydan Tokenizing | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | https://seneca.sharepoint.com/:w:/s/CPR101Mondays-Group1/ERSpFC3D5jROrjKQWEzUJ9MBfQuKJ-WWMRFUz5I3cMaShA?e=1iYZp6 |  | Thursday Nov.23 |  | * Notes * Version 1 development * Version 1 test examples * Upload final version to root folder | * PM-Notes-Alexander Raydan.docx * tokenizingv1_test_cases.xlsx * tokenizing.c * tokenizing.h (Done when approved by Tester) | 3.75 | Friday Nov.24 ---------- Firday Nov.24 | DONE | * Notes * Version 2 development * Version 2 test examples * Upload final version to git repository | * PM-Notes-Alexander Raydan.docx * tokenizingv2_test_cases.xlsx * tokenizing.c * tokenizing.h (Done when approved by Tester) | 3.25 | Sunday Nov.26 | DONE | * Notes * Version 3 development * Version 3 test examples * Upload final version to git repository | * PM-Notes-Alexander Raydan.docx * tokenizingv3_test_cases.xlsx * tokenizing.c * tokenizing.h (Done when approved by Tester) | 3.25 | Friday Dec.01 | DONE LATE |  |  |  | Tuesday Dec.12
Amirmohammad Shamshirishorbakhloo Conversions | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader |  |  | Thursday Nov.23 |  | * Notes * Version 1 development * Version 1 test examples * Upload final version to root folder | * PM-Notes-Amirmohammad Shamshirishorbakhloo.docx * conversionsv1_test_cases.xlsx * conversions.c * conversions.h (Done when approved by Tester) | 3.75 | Friday Nov.24 ---------- Firday Nov.24 | DONE | * Notes * Version 2 development * Version 2 test examples * Upload final version to git repository | * PM-Notes-Amirmohammad Shamshirishorbakhloo.docx * conversionsv2_test_cases.xlsx * conversions.c * conversions.h (Done when approved by Tester) | 3.25 | Sunday Nov.26 | DONE | * Notes * Version 3 development * Version 3 test examples * Upload final version to git repository | * PM-Notes-Amirmohammad Shamshirishorbakhloo.docx * conversionsv3_test_cases.xlsx * conversions.c * conversions.h (Done when approved by Tester) | 3.25 | Friday Dec.01 | DONE LATE |  |  |  | Wednesday Dec.13
Heungbin Oh Test Developer | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader |  |  | Thursday Nov.23 |  | * Notes * Version 1 test examples * version 1 module testing.txt | * Final-Project-Test-Cases.xlsx * main-testing.txt * fundamentals-testing.txt * manipulating-testing.txt * tokenizing-testing.txt * converting-testing.txt (Team lead reviews outputs) | 5.25 | Monday Nov.27 | DOING | * Notes * Version 2 test examples * version 2 module testing.txt | * Final-Project-Test-Cases.xlsx * main-testing.txt * fundamentals-testing.txt * manipulating-testing.txt * tokenizing-testing.txt * converting-testing.txt (Team lead reviews outputs) | 4.5 | Monday Nov.27 | DONE | * Notes * Version 3 test examples * version 3 module testing.txt | * Final-Project-Test-Cases.xlsx * main-testing.txt * fundamentals-testing.txt * manipulating-testing.txt * tokenizing-testing.txt * converting-testing.txt (Team lead reviews outputs) | 4.5 | Sunday Dec.03 | DONE LATE |  |  |  | ABSOLUTE DEADLINE
Jhonattan Gomez PM - Team Lead | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | https://seneca.sharepoint.com/:w:/s/CPR101Mondays-Group1/EWipWwG29r1OifS6EEeN7vgBca6RvcY-l53WooGK2uge7A?e=ASWwes |  | Thursday Nov.23 |  | * PM Notes * The Plan * Final plan meeting * Follow ups on team advancements * Git repository creation * Meeting for V1 Submission * Compiling of full version 1 * Submission V1 | * main.c * main-testing.txt * Final-Project-Test-Cases.xlsx * main-testing.txt * Final-Project-Plan.xlsx * Final-Project-Bb01.zip (The submission will be done with the whole team during a call) | 7.5 | Monday Nov.27 | TO DO | * PM Notes * Follow ups on team advancements * Git logs download * Meeting for V2 Submission * Compiling of full version 2 * Submission V2 | * main.c * main-testing.txt * Final-Project-Test-Cases.xlsx * main-testing.txt * Final-Project-Plan.xlsx * Final-Project-Bb01.zip (The submission will be done with the whole team during a call) | 3.5 | Monday Nov.27 | DONE | * PM Notes * Follow ups on team advancements * Git logs download * Meeting for V3 Submission * Compiling of full version 3 * Submission V3 | * main.c * main-testing.txt * Final-Project-Test-Cases.xlsx * main-testing.txt * Final-Project-Plan.xlsx * Final-Project-Bb01.zip (The submission will be done with the whole team during a call) | 3.5 | Monday Dec.04 | DONE LATE |  |  |  | no submissions accepted after this date
|  |  |  | Friday Nov.24 |  | "Work on [module name]" is not specific. There are tasks with a critical path. WBS? Filenames to be uploaded to your team's Files area. | What is the team's criteria for acceptance of development (files on developer's PC) when promoted to integration (Files in team's channel) What file names? What is definition of done / good enough? Who decides that? Project Overview and Programming Comments¦Testing docs have this information to be quoted or referenced. Requests for professor's review come after the team has accepted the work. |  | Wednesday Nov.29 |  |  |  |  | Monday Dec.4 |  |  |  |  | Monday Dec.11
|  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | DUE DATE upload to Blackboard
submissions after this date subject to extra time charge of 20% per day
Note on A1: Update ?? to your Blackboard group number and XYY to your CPR101XYY class code. Then press TAB to next set up item in E3.
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on E3: Change this to the date of your Project Management class and the worksheet will calculate all milestone dates.
Note on O6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We skipped straight to V3